## Sheet1
task | days | Duration | start | end
Literature Review | 21 | 21 | 1 | 21
Requirements Analysis | 35 | 14 | 21 | 35
Network Design | 42 | 7 | 35 | 42
Packet Tracer Setup | 49 | 7 | 42 | 49
OSPF Configuration | 49 | 3 | 49 | 49
PPP Configuration | 56 | 2 | 56 | 56
STP Configuration | 56 | 2 | 56 | 56
Testing & Verification | 77 | 21 | 56 | 77
Documentation | 84 | 7 | 77 | 84
Report Writing | 105 | 21 | 84 | 105
Final Review | 127 | 22 | 105 | 127